## Field-program
Field Program
|  |  |  | Type of UZ | Status |  |  | Duration | Score | Qty | Movement
Team | Division | District | Sub district | OLD/New | T/A | Start date | End date | Days | Points | UZ | Departure | Arrival
Team-1: Enumenator =7, Supervisor=1 | Rajshahi | Rajshahi | Puthia | new | T | 2022-11-21 | 2022-11-29 | 9 | 9 | 1 | Dhaka | Shibganj
|  | Chapai Nawabgang | Shibganj | new | T | 2022-11-30 | 2022-12-04 | 5 | 5 | 1 | Shibganj | Puthia
|  | Natore | Boraigram | old | T | 2022-12-05 | 2022-12-09 | 5 | 5 | 1 | Puthia | Boraigram
|  |  | Shingra | old | T | 2022-12-10 | 2022-12-16 | 7 | 7 | 1 | Boraigram | Shingra
|  | Bogra | Bogra Sadar | old | T | 2022-12-17 | 2022-12-21 | 5 | 5 | 1 | Shingra | Bogra Sadar
|  |  | Sariakandi | new | T | 2022-12-22 | 2022-12-26 | 5 | 5 | 1 | Bogra Sadar | Sariakandi
|  | Pabna | Chatmohar | new | T | 2022-12-27 | 2023-01-01 | 6 | 6 | 1 | Sariakandi | Shahjadpur
|  | Sirajganj | Shahjadpur | new | T | 2023-01-02 | 2023-01-05 | 4 | 4 | 1 | Shahjadpur | Chatmohar
| Khulna | Kushtia | Bheramara | old | T | 2023-01-06 | 2023-01-11 | 6 | 6 | 1 | Chatmohar | Bheramara
|  |  | Kushtia Sadar | old | T | 2023-01-12 | 2023-01-18 | 7 | 7 | 1 | Bheramara | Kushtia Sadar
[5 empty] | T | 2023-01-19 | 2023-01-19 | 1 | 1 | 1 | Kushtia Sadar | Dhaka
|  | T1 | Sub-total |  |  |  |  | 60 | 60 | 10
Team-2: Enumenator =6, Supervisor=1 | Rajshahi | Naogaon | Naogaon Sadar | new | T | 2022-11-21 | 2022-11-29 | 9 | 9 | 1 | Dhaka | Naogaon Sadar
|  | Joypurhat | Akkelpur | new | T | 2022-11-30 | 2022-12-04 | 5 | 5 | 1 | Naogaon Sadar | Akkelpur
| Rangpur | Gaibandha | Palashbari | new | T | 2022-12-05 | 2022-12-09 | 5 | 5 | 1 | Akkelpur | Parbatipur
|  | Dinajpur | Biral | new | T | 2022-12-10 | 2022-12-16 | 7 | 7 | 1 | Parbatipur | Biral
|  |  | Parbatipur | old | T | 2022-12-17 | 2022-12-20 | 4 | 4 | 1 | Biral | Palashbari
|  | Thakurgaon | Thakurgaon Sadar | new | T | 2022-12-21 | 2022-12-25 | 5 | 5 | 1 | Palashbari | Mithapukur
|  | Panchagarh | Debiganj | new | T | 2022-12-26 | 2022-12-31 | 6 | 6 | 1 | Mithapukur | Kaunia
|  | Rangpur | Mithapukur | old | T | 2023-01-01 | 2023-01-04 | 4 | 4 | 1 | Kaunia | Debiganj
|  |  | Kaunia | old | T | 2023-01-05 | 2023-01-10 | 6 | 6 | 1 | Debiganj | Thakurgaon Sadar
[5 empty] | T | 2023-01-11 | 2023-01-11 | 1 | 1 | 1 | Thakurgaon Sadar | Dhaka
|  | T2 | Sub-total |  |  |  |  | 52 | 52 | 9
Team-3: Enumenator =7, Supervisor=1 | Khulna | Magura | Magura Sadar | new | T | 2022-11-21 | 2022-11-29 | 9 | 9 | 1 | Dhaka | Satkhira Sadar
|  | Jessore | Jessore Sadar | old | T | 2022-11-30 | 2022-12-04 | 5 | 5 | 1 | Satkhira Sadar | Tala
|  |  | Monirampur | old | T | 2022-12-05 | 2022-12-09 | 5 | 5 | 1 | Tala | Monirampur
|  | Jhenaidah | Harinakunda | new | T | 2022-12-10 | 2022-12-16 | 7 | 7 | 1 | Monirampur | Jessore Sadar
|  |  | Kaliganj | old | T | 2022-12-17 | 2022-12-21 | 5 | 5 | 1 | Jessore Sadar | Magura Sadar
|  | Chuadanga | Alamdanga | new | T | 2022-12-22 | 2022-12-26 | 5 | 5 | 1 | Magura Sadar | Harinakunda
|  | Meherpur | Meherpur Sadar | new | T | 2022-12-27 | 2023-01-01 | 6 | 6 | 1 | Harinakunda | Kaliganj
|  | Narail | Narail Sadar | new | T | 2023-01-02 | 2023-01-05 | 4 | 4 | 1 | Kaliganj | Narail Sadar
|  | Satkhira | Satkhira Sadar | old | T | 2023-01-06 | 2023-01-11 | 6 | 6 | 1 | Narail Sadar | Meherpur Sadar
|  |  | Tala | old | T | 2023-01-12 | 2023-01-18 | 7 | 7 | 1 | Meherpur Sadar | Alamdanga
[5 empty] | T | 2023-01-19 | 2023-01-19 | 1 | 1 | 1 | Alamdanga | Dhaka
|  | T3 | Sub-total |  |  |  |  | 60 | 60 | 10
Team-4: Enumenator =7, Supervisor=1 | Dhaka | Dhaka | Dhamrai | old | T | 2022-11-21 | 2022-11-29 | 9 | 9 | 1 | Dhaka | Rajbari Sadar
|  |  | Dohar | new | T | 2022-11-30 | 2022-12-04 | 5 | 5 | 1 | Rajbari Sadar | Kalukhali
|  | Manikganj | Singair | new | T | 2022-12-05 | 2022-12-09 | 5 | 5 | 1 | Kalukhali | Singair
|  | Munshiganj | Gazaria | new | T | 2022-12-10 | 2022-12-16 | 7 | 7 | 1 | Singair | Dhamrai
|  | Norshingdi | Raipura | new | T | 2022-12-17 | 2022-12-21 | 5 | 5 | 1 | Dhamrai | Madhupur
|  |  | Shibpur | old | T | 2022-12-22 | 2022-12-26 | 5 | 5 | 1 | Madhupur | Dhanbari
|  | Rajbari | Rajbari Sadar | old | T | 2022-12-27 | 2023-01-01 | 6 | 6 | 1 | Dhanbari | Shibpur
|  |  | Kalukhali | new | T | 2023-01-02 | 2023-01-05 | 4 | 4 | 1 | Shibpur | Raipura
|  | Tangail | Dhanbari | new | T | 2023-01-06 | 2023-01-11 | 6 | 6 | 1 | Raipura | Araihazar
|  |  | Madhupur | old | T | 2023-01-12 | 2023-01-18 | 7 | 7 | 1 | Araihazar | Gazaria
|  | Narayanganj | Araihazar | new | T | 2023-01-19 | 2023-01-23 | 5 | 5 | 1 | Gazaria | Dohar
[5 empty] | T | 2023-01-24 | 2023-01-24 | 1 | 1 | 1 | Dohar | Dhaka
|  | T4 | Sub-total |  |  |  |  | 56 | 56 | 11
Team-5: Enumenator =6, Supervisor=1 | Khulna | Khulna | Dumuria | old | T | 2022-11-21 | 2022-11-29 | 9 | 9 | 1 | Dhaka | Bhola Sadar
|  |  | Paikgacha | old | T | 2022-11-30 | 2022-12-04 | 5 | 5 | 1 | Bhola Sadar | Nazirpur
|  | Bagerhat | Bagerhat Sadar | new | T | 2022-12-05 | 2022-12-09 | 5 | 5 | 1 | Nazirpur | Bagerhat Sadar
| Barishal | Bhola | Bhola Sadar | new | T | 2022-12-10 | 2022-12-16 | 7 | 7 | 1 | Bagerhat Sadar | Dumuria
|  | Pirojpur | Nazirpur | new | T | 2022-12-17 | 2022-12-21 | 5 | 5 | 1 | Dumuria | Paikgacha
| Dhaka | Madaripur | Shibchar | new | T | 2022-12-22 | 2022-12-26 | 5 | 5 | 1 | Paikgacha | Kotalipara
|  | Shariatpur | Zajira | new | T | 2022-12-27 | 2023-01-01 | 6 | 6 | 1 | Kotalipara | Shibchar
|  | Faridpur | Faridpur Sadar | old | T | 2023-01-02 | 2023-01-05 | 4 | 4 | 1 | Shibchar | Zajira
|  |  | Bhanga | new | T | 2023-01-06 | 2023-01-11 | 6 | 6 | 1 | Zajira | Bhanga
|  | Gopalgonj | Kotalipara | new | T | 2023-01-12 | 2023-01-18 | 7 | 7 | 1 | Bhanga | Faridpur Sadar
[5 empty] | T | 2023-01-19 | 2023-01-19 | 1 | 1 | 1 | Faridpur Sadar | Dhaka
|  | T5 | Sub-total |  |  |  |  | 60 | 60 | 10
Team-6: Enumenator =5, Supervisor=1 | Mymensingh | Mymensingh | Nandail | new | T | 2022-11-21 | 2022-11-29 | 9 | 9 | 1 | Dhaka | Kaliakoir
|  |  | Trishal | old | T | 2022-11-30 | 2022-12-04 | 5 | 5 | 1 | Kaliakoir | Kaligonj
|  | Sherpur | Jhenaigati | new | T | 2022-12-05 | 2022-12-09 | 5 | 5 | 1 | Kaligonj | Trishal
|  |  | Sreebordi | old | T | 2022-12-10 | 2022-12-16 | 7 | 7 | 1 | Trishal | Nandail
|  | Jamalpur | Islampur | new | T | 2022-12-17 | 2022-12-21 | 5 | 5 | 1 | Nandail | Jhenaigati
|  | Netrokona | Kendua | new | T | 2022-12-22 | 2022-12-26 | 5 | 5 | 1 | Jhenaigati | Sreebordi
| Dhaka | Gazipur | Kaliakoir | old | T | 2022-12-27 | 2023-01-01 | 6 | 6 | 1 | Sreebordi | Kendua
|  |  | Kaligonj | new | T | 2023-01-02 | 2023-01-05 | 4 | 4 | 1 | Kendua | Islampur
|  | Kishoreganj | Bhairab | old | T | 2023-01-06 | 2023-01-11 | 6 | 6 | 1 | Islampur | Bhairab
|  |  | Hossainpur | new | T | 2023-01-12 | 2023-01-18 | 7 | 7 | 1 | Bhairab | Hossainpur
[5 empty] | T | 2023-01-19 | 2023-01-19 | 1 | 1 | 1 | Hossainpur | Dhaka
|  | T6 | Sub-total |  |  |  |  | 60 | 60 | 10
Team-7: Enumenator =6, Supervisor=1 | Chittagong | Bandarban | Bandarban Sadar | new | T | 2022-11-21 | 2022-11-29 | 9 | 9 | 1 | Dhaka | Kutubdia
|  | Chandpur | Chandpur Sadar | old | T | 2022-11-30 | 2022-12-04 | 5 | 5 | 1 | Kutubdia | Banshkhali
|  |  | Kachua | new | T | 2022-12-05 | 2022-12-09 | 5 | 5 | 1 | Banshkhali | Mirsharai
|  | Chittagong | Banshkhali | new | T | 2022-12-10 | 2022-12-16 | 7 | 7 | 1 | Mirsharai | Khagrachhari Sadar
|  |  | Mirsharai | old | T | 2022-12-17 | 2022-12-21 | 5 | 5 | 1 | Khagrachhari Sadar | Bandarban Sadar
|  | Khagrachhari | Khagrachhari Sadar | new | T | 2022-12-22 | 2022-12-26 | 5 | 5 | 1 | Bandarban Sadar | Rangamiti Sadar
|  | Cox's Bazar | Kutubdia | new | T | 2022-12-27 | 2023-01-01 | 6 | 6 | 1 | Rangamiti Sadar | Fulgazi
|  | Feni | Fulgazi | new | T | 2023-01-02 | 2023-01-05 | 4 | 4 | 1 | Fulgazi | Companiganj
|  | Noakhali | Companiganj | new | T | 2023-01-06 | 2023-01-11 | 6 | 6 | 1 | Companiganj | Raipur
|  | Laxmipur | Raipur | new | T | 2023-01-12 | 2023-01-18 | 7 | 7 | 1 | Raipur | Chandpur Sadar
|  | Rangamati | Rangamiti Sadar | new | T | 2023-01-19 | 2023-01-22 | 4 | 4 | 1 | Chandpur Sadar | Kachua
[5 empty] | T | 2023-01-23 | 2023-01-23 | 1 | 1 | 1 | Kachua | Dhaka
|  | T7 | Sub-total |  |  |  |  | 55 | 55 | 11
Team-8: Enumenator =5, Supervisor=1 | Sylhet | Habiganj | Baniyachong | new | T | 2022-11-21 | 2022-11-29 | 9 | 9 | 1 | Dhaka | Derai
|  | Moulavibazar | Juri | new | T | 2022-11-30 | 2022-12-04 | 5 | 5 | 1 | Derai | Sylhet Sadar
|  |  | Sreemangal | old | T | 2022-12-05 | 2022-12-09 | 5 | 5 | 1 | Sylhet Sadar | Dakshin Surma
|  | Sunamganj | Derai | new | T | 2022-12-10 | 2022-12-16 | 7 | 7 | 1 | Dakshin Surma | Sreemangal
|  | Sylhet | Dakshin Surma | old | T | 2022-12-17 | 2022-12-21 | 5 | 5 | 1 | Sreemangal | Juri
|  |  | Sylhet Sadar | old | T | 2022-12-22 | 2022-12-26 | 5 | 5 | 1 | Juri | Baniyachong
| Chittagong | B. Baria | B. Baria Sadar | old | T | 2022-12-27 | 2023-01-01 | 6 | 6 | 1 | Baniyachong | B. Baria Sadar
|  |  | Nasirnagar | new | T | 2023-01-02 | 2023-01-05 | 4 | 4 | 1 | B. Baria Sadar | Nasirnagar
|  | Comilla | Chandina | old | T | 2023-01-06 | 2023-01-11 | 6 | 6 | 1 | Nasirnagar | Chandina
|  |  | Debidwar | new | T | 2023-01-12 | 2023-01-18 | 7 | 7 | 1 | Chandina | Debidwar
[6 empty] | 2023-01-19 | 2023-01-19 | 1 | 1 | 1 | Debidwar | Dhaka
|  | T7 | Sub-total |  |  |  |  | 60 | 60 | 10
|  | All Team | Total |  |  |  |  | 463 | 463 | 81